## Sheet1
Budget for An Action Plan for TB and Poverty (All figures in US Dollars)
DOC 1.06-7.2
Activities | Responsible Agencies | Year |  |  |  |  | Totals by ouput | expected provision by Subgroup | GRAND TOTAL
|  | 2006 |  | 2007 |  | TOTALS
Output 1 | Lead:
An inventory of existing strategies for addressing poverty and enhancing equity in health service delivery appraised for their relevance to implementation of the STOP-TB Strategy. | CSDH | [5 empty] | 22400 | 50000 | 72400
a. Identification of key organizations working on equitable health service delivery and linkages established through active networking via STOP-TBPartnership | All partners through Secretariat
Part of Secretariat function |  |  | 0 |  |  | 0
b. Compilation of information on strategies tackling poverty in health service delivery and assessment of their appropriateness for application to TB control | WB
Costs for an individual at WB (further details on discussion between Birte Sorensen and Ritu Sadana) |  |  | 5000 | 5000 |  | 10000
c. Appraisal of indicators and methodologies used in evaluating equity-enhancing strategies (to feed into Output 2) | BRAC CSDH LSTM
15 days desk work per 6 months (Associate Researchers, BRAC and LSTM |  |  | 6000 | 6000 |  | 12000
Communication (phone, email & internet) |  |  | 200 | 200 |  | 400
Output 2 | STB | [5 empty] | 145200
A set of indicators and methodologies for assessing equity of access and financial protection that can be used as part of the evaluation of TB control | [7 empty] | 50000 | 195200
a. Working with stakeholders to define the relevant measurable indicators of poverty | WHO Health Equity Team, BRAC, KNCV Research, BRACH, REACH
15 days desk work per 6 months (Researchers, BRAC, REACH, LSTM, WHO HET) |  | 6000 | 6000 |  |  | 12000
Communication (phone, email & internet) |  | 200 | 200 |  |  | 400
b. Develop standardized processes to collect data on socio-economic profiles of patients in TB prevalence surveys in order to allow nested case-control comparisons between patients identified in the community who do not access TB control and those who do.
20 days desk work per 6 months (Staff time EPI-LAB, REACH, BRAC, LSTM, KNCV Research) |  |  | 8000 | 8000 |  | 16000
Communication (phone, email & internet) |  |  | 200 | 200 |  | 400
c. Design surveys of patients currently registered in TB control programmes to capture socioeconomic profiles, data on treatment delay, and data on health expenditure
20 days desk work per 6 months (REACH, BRAC, EPI-LAB, KNCV Research) |  |  | 8000 | 8000 |  | 16000
Communication (phone, email & internet) |  |  | 200 | 200 |  | 400
3 day workshop to finalise consensus document on indicators and methodologies |  |  |  | 100000 |  | 100000
Output 3 | REACH and t.b.c | [5 empty] | 132800 | 0 | 132800
Documentation of the special access barriers and financial burden faced by patients with TB/HIV co-infection and MDR-TB.
a. Review of existing literature and evidence in collaboration with TB-HIV working group to identify gaps | REACH
20 days desk work per 6 months (Researcher, REACH) |  | 8000 | 8000 |  |  | 16000
Communication (phone, email & internet) |  | 200 | 200 |  |  | 400
b. Review of existing literature and evidence in collaboration with MDR-TB working group to identify gaps
20 days desk work per 6 months (Researcher, to be identified) |  | 8000 | 8000 |  |  | 16000
Communication (phone, email & internet) |  | 200 | 200 |  |  | 400
c. Further work to fill gaps in knowledge
1 day workshop with key representatives of Implementation Working Groups to scrutinise literature reviews and agree further research agenda |  |  |  | 100000 |  | 100000
Output 4 | The Union and KNCV International
Enhanced capacity and technical assistance for implementing and evaluating pro-poor strategies in TB control | [6 empty] | 230000 | 60000 | 290000
a. Networking with partners and donors in order to assess necessary capacity needed for implementing and evaluating pro-poor TB control. | KNCV International
Part of Core Team and Secretariat function |  | 0 | 0 |  |  | 0
b. Developing and delivering training courses for the use of the existing TB & Poverty Manual | The Union
Development of course material |  | 100000 |  |  |  | 100000
Consultative workshops |  |  | 100000 |  |  | 100000
Finalisation of training module |  |  |  | 30000 |  | 30000
Output 5 | KNCV through DEWG and others | [5 empty] | 60000
Evaluation of the equity-enhancing effects of existing interventions (e.g. Public-Private Mix [PPM], Practical Approach to Lung Health [PAL]) | [7 empty] | 0 | 60000
a. Assessing equity effectiveness and economic evaluation of model interventions (using indicators and methodologies developed under (2)) | STB
Following GDF evaluation model. USD 5,000 per evaluation, 2 evaluations per year. |  |  |  |  | 10000 | 10000
a. Process and in-depth evaluation of model interventions to capture impact and key lessons learned in implementation (e.g. training needs and training approaches) | LSTM
One in-depth evaluation per country per year |  |  |  |  | 50000 | 50000
Output 6 | FIND | [5 empty] | 111000 | 100000 | 211000
Strategies to enhance equitable access to the new tools for TB control through the New tools Working Groups of the STOP-TB Partnership.
a. Review of existing global access strategies for new tools being developed through Private – Public Partnerships (diagnostics, drugs, vaccines)
5 days desk work per 6 months (Associate Researcher, LSTM) |  | 2000 | 2000 |  |  | 4000
Communication (phone, email & internet) |  | 200 | 200 |  |  | 400
b. Appraisal of new tools access strategies for relevance against current pro-poor modalities of delivery of TB control (PPM, PAL, TB-HIV)
5 days desk work per 6 months (Associate Researcher, LSTM) |  |  | 2000 | 2000 | 2000 | 6000
Communication (phone, email & internet) |  |  | 200 | 200 | 200 | 600
1 day workshop with key members of all New Tools Working Groups to finalise consensus document on new tools access strategies |  |  |  |  | 100000 | 100000
Output 7 | The Union | [5 empty] | 470000 | 100000 | 570000
Development of new pro-poor approaches relevant to the implementation of the Stop TB Strategy
a. Compilation of Outputs 1-6 to develop new, evidence-based approaches for pro-poor delivery of TB Control
3 day workshop to synthesise experience from Outputs 1-6 | REACH, BRAC, EPILAB |  |  |  | 200000 | 200000
Pilot testing of training modules including establishment of pilot projects in 3 HBCs; | The Union |  |  |  | 180000 | 180000
Evaluation of training and pilot projects | The Union |  |  |  | 90000 | 90000
Totals |  | 124800 | 154600 | 259800 | 632200 | 1171400 | 1171400 | 360000 | 1531400