## Summary
Stop TB Secretariat Workplan Overview |  |  |  | BUDGET
Area of Work | Objectives | Products | Timeline | Staff cost | Cost of Activities | Budget
(1) Partnership | 1. To sustain and enhance the global partnership to Stop TB | 1.1 Enhance performance of global partners |  | 138312 | 976320 | 1114632
| 2. To establish and expand regional and national partnerships | 2.1 Functional expanded regional partnerships |  | 63732 | 248600 | 312332
|  | 2.2 Functional expanded national partnerships in all 22 HBC |  | 65088 | 90400 | 155488
| 3. To increase synergy of output between the Working Groups in support of reaching the Global Plan 2005 targets | 3.1 Joint outputs of all Working Groups in support of reaching the Global Plan 2005 targets |  | 51528 | 53675 | 105203
| 4. To stimulate and support current and new partners to contribute towards reaching the 2005 Global Plan targets | 4.1 Contributions of current and new partners are in line with the reaching of the 2005 Global Plan targets |  | 97632 | 39550 | 137182
| 5. To monitor the progress of the Global Plan to Stop TB | 5.1 Annual Status Report on the progress of the Global Plan to Stop TB |  | 50172 | 33900 | 84072
| 6. To increase the flow of resources in support of reaching the Global Plan targets | 6.1 Increase of resource flow to meet the Global Plan targets |  | 143736 | 31075 | 174811
|  | Total for Partnerships |  | 610200 | 1473520 | 2083720
(2) Global TB Drug Facility | 1. Facilitate DOTS expansion: supply 2.8 million patient treatments | 1.1 Demand assessment and demand creation for GDF services (grants and direct procurement) |  | 54918 | 67800 | 122718
|  | 1.2 Application and review process for GDF grants |  | 134244 | 129950 | 264194
|  | 1.3 Whitelist of pre-qualified manufacturers of quality TB products |  | 31188 | 350300 | 381488
|  | 1.4 Coordination of GDF supply agents and monitoring agents |  | 62376 | 467707 | 530083
|  | 1.5 Grants of first line TB drugs for GDF |  | 176280 | 40089800 | 40266080 | *
| 2. Catalyse improvements in national and international TB drug manufacturing and rational use | 2.1 Global TB drug market survey |  | 25764 | 62150 | 87914
|  | 2.2 Product packaging development |  | 27120 | 0 | 27120
| 3. Facilitate improvements in monitoring of DOTS programmes | 3.1 GDF monitoring to ensure compliance with GDF terms and conditions |  | 121362 | 56500 | 177862
| 4. Facilitate improvements in drug management in DOTS programmes | 4.1 Strengthened national TB drug management |  | 65088 | 22600 | 87688
| 5. Expand the GDF scope to include products for diagnosis of TB, and treatment of Malaria and TB-HIV | 5.1 Pre-qualification of suppliers of diagnostics equipment and non-consumables |  | 27120 | 129950 | 157070
|  | 5.2 An expanded GDF catalogue to include products for the diagnosis of TB, and treatment of malaria and TB-HIV |  | 52206 | 0 | 52206
|  | 6.1 GDF Advocacy and Resource Mobilization |  | 46104 | 113000 | 159104
|  | 7.1 GDF internal management |  | 183060 | 0 | 183060
|  | Total for GDF |  | 1006830 | 41489757 | 42496587
(3) Advocacy and Communications | 1. Identify advocacy and communications priorities for the Stop TB Partnership at global and regional levels | 1.1 Strategic guidance for advocacy and communications |  | 27120 | 146900 | 174020
|  | 1.2 Media and political advocacy |  | 47460 | 452000 | 499460
| 2. Plan, organize and coordinate advocacy & communications activities to support the global Stop TB mission | 2.1 World TB Day |  | 44748 | 175150 | 219898
|  | 2.2 Public awareness and information dissemination |  | 26442 | 158200 | 184642
| 3. Develop mechanisms to address information needs of Stop TB Partners | 3.1 Information mechanism/IT support |  | 261708 | 237300 | 499008
| 4. Develop mechanisms to provide advocacy & communications support at country level | 4.1 Community mobilization to support DOTS expansion |  | 70512 | 316400 | 386912
| 5. Develop and implement partnership mechanisms to evaluate the effectiveness of advocacy & communications efforts | 5.1 Evaluation, assessment and documentation |  | 40680 | 5650 | 46330
|  | Total for Advocacy and Communication |  | 518670 | 1491600 | 2010270
(4) Administration | 1. To facilitate the management of the Global Partnership through the support of its governing structures | 1.1 Administrative and logistical management of the partnership |  | 386460 | 50850 | 437310
|  | Total for Administration |  | 386460 | 50850 | 437310
|  | TOTAL WORKPLAN COST (FTEs=25.7) |  | 2522160 | 44505727 | 47027887
Note:
* 50% of the budget expected to be through GDF and 50% will be direct procurement supported from funds from national sources, GFATM and donors

## PARTNERSHIP
Stop TB Work Plan 2003
1 | Area of Work: Partnership
| NARRATIVE | 2003 | 2003
| Purpose | Jan | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Timeline | Linkages | Indicators | Targets 2003 | Means of Verification | Assumptions & Risks
| To support Stop TB Partners in the fulfilment of the vision and mission of the global partnership | [56 empty] | State of the World's Effort to Stop TB 2003 | Case detection in DOTS areas of 50% and cure rate of 85% | Publication
Objectives
| 1. To sustain and enhance the global partnership to Stop TB | [56 empty] | Number of partners actively participating to the Forum | 10% of forum presentations are from new partners | Agenda and number of active participants
| 2. To establish and expand regional and national partnerships | [56 empty] | Number of Working Regional and National Partnerships | Regional Partnerships have global coverage | Semi-annual reports
| 3. To increase synergy of output between the Working Groups in support of reaching the Global Plan 2005 targets | [56 empty] | Number of Joint activities | Each WG is operationally linked in support of Global Plan | Semi-annual reports
| 4. To stimulate and support current and new partners to contribute towards reaching the 2005 Global Plan targets | [56 empty] | Contributions from partners to reach global targets | Compared with 2001 status, 50% increase of contributions from partners | Partners Directory
| 5. To monitor the progress of the Global Plan to Stop TB | [56 empty] | State of the World's Effort to Stop TB 2003 | Publish on World TB Day | Publication & Partners Forum
| 6. To increase the flow of resources in support of reaching the Global Plan targets | [56 empty] | International and national flow of resources | 25% increase of 2001 levels | Annual review of financial contributions
Products and Activities
| 1.1 Enhance performance of global partners | [56 empty] | Number of partners actively participating to the Forum | 10% of forum presentations are from new partners | Meeting and evaluation reports | Lack of interest for new partners to actively join
1.1.1 | Coordinating Board Meetings and teleconferences held at regular intervals through support of the Secretariat |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  | Jan-Dec
1.1.2 | Evaluation of the Global Partnership to Stop TB | [36 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Sep-Dec(up to 1st Q 2004)
1.1.3 | Stop TB Partners Forum, 2003 | [12 empty] | x | x | [6 empty] | x |  |  |  |  | x |  |  |  |  | x |  |  |  | x | [9 empty] | x | x | x | x | x | [5 empty] | Jan-Dec
| 2.1 Functional expanded regional partnerships | [56 empty] | Number of Working Regional Partnerships | 6 regional partnerships | Semi-annual reports
2.1.1 | Regional partnership IT support for establishing directories | [15 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | [26 empty] | April-June
2.1.2 | Regional meetings to engage more partners |  | x | x | x | x | x | x | x | x | x | [26 empty] | x | x | x | x | x | [13 empty] | Jan-Feb and Sept | 6.1.3
2.1.3 | Building regional partnership |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec | 6.1.3
| 2.2 Functional expanded national partnerships in all 22 HBC | [56 empty] | Number of Working National Partnerships | 22 HBC partnerships and 6 partnerships in other countries | Semi-annual reports | The commitment to DOTS Expansion is the basic assumption.The capabilities to run a partnership secretariat are assumed. The lack of partners' participation is a potential risk, also communicative skills of the partnership facilitator at the secretariat.
2.2.1 | Pilot national partnerships IT and logistical support |  | x | x | x | x | x | [17 empty] | x | x | x | x | x | [26 empty] | Jan and June
2.2.2 | National meetings in 22 HBC to engage more partners on the Expanded Framework for DOTS Expansion |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
2.2.3 | Strengthen the NICC/CCM through country visits |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
| 3.1 Joint outputs of all Working Groups in support of reaching the Global Plan 2005 targets | [56 empty] | Number of Joint activities | Each WG has at least 2 joint activities with other WGs | Semi-annual reports | Willingness to work together is assumed and commitment to global Plan a requirement. The risks are mainly in the field of joint activities, when credits for work/output and funding are underlying issues.
3.1.1 | Support to monitoring of WG's progress and output |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [14 empty] | Jan-Sept
3.1.2 | Annual Joint Meetings for all WG chairs and secretariats to harmonise and focus respective agendas | [25 empty] | x | x | x | [26 empty] | June
3.1.3 | Linking Research WG activities with country based DOTS Expansion |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
| 4.1 Contributions of current and new partners are in line with the reaching of the 2005 Global Plan targets | [56 empty] | Contributions from partners to reach 2005 global targets | Compared with 2001 status, 50% increase of contributions from partners | Partners Directory | The willingness and ability of partners to contribute is assumed. The risk is the willingness by partners to accept Partnership suggestions for funding or support.
4.1.1 | Mobilize partners through partners directory |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
4.1.2 | Publish annual overview of partners financial contributions |  | x | x | x | x | x | x | x | x | x | [22 empty] | x | x | x | x | [18 empty] | Jan-Feb and Aug
4.1.3 | Develop close working relationship with other global initiatives and partnerships (including the GFATM) |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | xx | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec | 6.1.5
4.1.4 | Informational package for donors and other agencies on reaching the global targets, including corporate sector |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [35 empty] | Jan-Apr | 6.1.1
4.1.5 | Negotiate strategic alignments with donors to synergise inputs |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec | 6.1.3, 6.1.5
| 5.1 Annual Status Report on the progress of the Global Plan to Stop TB | [56 empty] | Report published in time for WTB Day 2003 | Report published in time for WTBD 2003 | Publication & Partners Forum | The timely availability of the input data and the related clearance by WH and CB are assumed. The risks are the contractual writers and the consensus among CB members on the final contents
5.1.1 | Production of the TB and Poverty booklet as input to the State of the World's Efforts to Stop TB, 2003 |  | x | x | x | x | x | x | x | x | x | [44 empty] | Jan-Feb
5.1.2 | Writing and production of the State of the World's Effort to Stop TB, 2004 |  | x | x | x | x | x | x | x | x | x | [44 empty] | Jan-Feb
| 6.1 Increase of resource flow to meet the Global Plan targets | [56 empty] | International and national flows of resources | 25% increase of 2001 levels | Annual review of financial contributions | Assumptions: Political commitment among donor agencies and contributing partners to make additional resources available. The continued political commitment from all partners and donor agencies to continue their previously declared support for the Amsterda
6.1.1 | Increase the advocacy and resource mobilization activities in meeting the funding gap requirements |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec | 4.1.4
6.1.2 | Facilitating the implementation of the RM guidelines at both Regional and National levels |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec | 2.1.2, 2.1.3, 2.2.3
6.1.3 | Inviting more partners at Regional Level meetings dealing on Resource Mobilization | X | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
6.1.4 | Resource Mobilization Directory contact booklet developed and updated regularly per region |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [31 empty] | Jan-May | 1.1.2
6.1.5 | Countries needs determined for STBP support/information in line with their resource mobilization efforts. |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [13 empty] | Jan-Sept | 3.1.2, 6.1.3
6.1.6 | Facilitating financing of partnership and working groups activites through various channels |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec | 4.1.2

## GDF
Stop TB Work Plan 2003
2 | Area of Work: Global TB Drug Facility
| NARRATIVE | 2003
| Purpose | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Timeline 2003 | Linkages | Indicators | Targets for 2003 | Means of Verification | Assumptions & Risks
| The mission of the GDF is to secure access to high quality TB drugs, in support of the global TB control targets for 2005 (and subsequently the Millenium Development Goals for 2015). The GDF goals of the GDF are to: * Ensure uninterrupted access to quality TB drugs for DOTS implementation. * Catalyze rapid DOTS expansion in order to achieve global TB targets * Stimulate political and popular support in countries worldwide for public funding of TB drug supplies * Secure sustainable global TB control and eventual elimination | [55 empty] | (a) Global population coverage with DOTS strategy end 2005 (b) Global DOTS case detection rate for 2005 (c) Global DOTS treatment success rate for 2005 (d) Trends in global funding for TB control 2001-2005 | DOTS case detection: 50% DOTS treatment success: 85% | WHO annual report on Global TB epidemic | * Drug shortages are a major constraint to accelerated DOTS expansion * Support from the GDF will catalyse additional resources for non-drug related aspects of DOTS expansion
Objectives for 2003
| 1. Facilitate DOTS expansion: supply 2.8 million patient treatments | [55 empty] | Number of people treated with drugs supplied by GDF | Grants: 1.4 million patients Direct procurement: 1.4 million patients | GDF database | * Countries have capacity to absorb and utilise TB drugs effectively
| 2. Catalyse improvements in national and international TB drug manufacturing and rational use | [55 empty] | (a) Proportion of global market for TB drugs produced by prequalified manufacturers (b) Proportion of DOTS patients treated with products on GDF product list (c) Proportion of DOTS patients treated with drugs supplied in blister packaged patient packs | (a) at least 10% of TB patients globally to be treated with products of known quality from prequalified manufacturers (b) at least 25% of TB patients globally to be treated with products which are on the GDF product list (c) at least 10% of TB patients globally to be treated with products supplied in plister packaged patient packs | TB drug market survey 2003 | * Poor quality products are widespread, and pose a major threat to TB control * Standardisation of products will increase the efficiency of procurement, and the effectiveness of treatment
| 3. Facilitate improvements in monitoring of DOTS programmes | [55 empty] | Proportion of GDF supported countries having an independent annual audit of TB programme performance | 100% | GDF database | Standardised monitoring tools required for objective assessment of adherence to GDF conditions of support
| 4. Facilitate improvements in drug management in DOTS programmes | [55 empty] | Frequency of stock out of any TB drugs in GDF supported countries | None | GDF monitoring reports | Assumes countries have capacity to implement effective drug management plans
| 5. Expand the GDF scope to include products for diagnosis of TB, and treatment of Malaria and TB-HIV | [55 empty] | Numbers of products in GDF catalogue for TB diagnosis, and treatment of Malaria & TB-HIV | At least one additional product in each area | GDF database | Assumes GDF feasibility study and GDF evaluation will indicate potential for expanded scope
Products and Activities
| 1.1 Demand assessment and demand creation for GDF services (grants and direct procurement) | [55 empty] | Funding gap for first and second line TB drugs and diagnostics in countries | No funding gaps for first line TB drugs in GDF eligible countries | Global DOTS Expansion Plan | Resource savailable for meeting funding gaps from national resources, GDF, GFATM and other donors
1.1.1 | Assess demand for first line TB drugs and resource gaps in GDF priority countries | x | x | x | x | x | x | x | x | [45 empty] | Jan-Feb
1.1.2 | Establish procedures for use of Direct Procurement by international agencies including GFATM, World Bank, regional banks and other major donors | x | x | x | x | x | x | x | x | [45 empty] | Jan-Feb
1.1.3 | Coordinate applications with GFATM secretariat | x | x | x | x | x | x | x | x | [7 empty] | x | x | x | x | x | x | x | x | x | x | x | [6 empty] | x | x | x | x | x | x | x | x | x | x | x | [7 empty] | x | x | x | Jan-Feb, April-June, Aug-Oct, Dec
1.1.4 | Assess demand for diagnostics | x | x | x | x | x | x | x | x | [45 empty] | Jan-Feb
1.1.5 | Invite applications to GDF grants for first line TB drugs and diagnostics, and for direct procurement | x | [14 empty] | x | [16 empty] | x | [20 empty] | Jan, Apr, Aug
1.1.6 | Assess demand for second line drugs in collaboration with GLC | x | x | x | x | x | x | x | x | [45 empty] | Jan-Feb
1.1.7 | Collaborate with GLC in applications and review for second line drugs | x | [8 empty] | x | [8 empty] | x | [8 empty] | x | [7 empty] | x | [8 empty] | x | [8 empty] | Jan, Mar, May, Jun, Aug, Nov
| 1.2 Application and review process for GDF grants | [55 empty] | Lead time from receipt of application to placement of order | 60 days | GDF database | * Number of rounds of application and review may increase depending on results of lead time assessment * Number of new applications likely to decrease as majority of priority countries approved for support
1.2.1 | Accept applications for first line TB drugs (and diagnostics) and applications for direct procurement | x | x | x | x | x | x | x | x | [8 empty] | x | x | x | x | x | x | x | x | x | x | x | [6 empty] | x | x | x | x | x | x | x | x | x | x | [7 empty] | x | x | x | Jan-Feb, Apr-June, Aug-Oct, Dec
1.2.2 | Screening of applications for grants and direct procurement | [8 empty] | x | x | [17 empty] | x | x | [14 empty] | x | x | [8 empty] | Feb, Jun, Oct
1.2.3 | Review of grant applications by GDF technical review committee | [10 empty] | x | [18 empty] | x | [15 empty] | x | [7 empty] | Jan-Dec
1.2.4 | Country visits | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
1.2.5 | Grant agreements | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
1.2.6 | Develop application mechanism for TB diagnostics | [9 empty] | x | x | x | x | x | x | [38 empty] | Feb-Mar
| 1.3 Whitelist of pre-qualified manufacturers of quality TB products | [55 empty] | Number of pre-qualified products & manufacturers meeting WHO GMP standards | At least 5 prequalified manufacturers for each GDF product | GDF/EDM published whitelist of products & manufacturers | * Adequate numbers of companies capable of producing products to meet WHO GMP standards * Capacity of EDM/QSM and inspectors to conduct document reviews and site inspections
1.3.1 | Publication of first whitelist of pre-qualified TB manufacturers through 2001 GDF-EDM/QSM project | x | x | x | x | x | [48 empty] | Jan
1.3.2 | Issue second General Procurement Notice inviting expressions of interest (EOI) to supply TB products |  |  | x | x | x | x | x | [46 empty] | Jan-Feb
1.3.3 | Receipt of EOIs and issuance of Guidelines for Dossier Submission by EDM/QSM | [7 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | [33 empty] | Feb-May
1.3.4 | Review of product dossiers from suppliers by EDM/QSM | [20 empty] | x | x | x | x | x | [28 empty] | May-June
1.3.5 | GMP physical site audits of eligible manufacturers | [25 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [10 empty] | Jun-Oct
1.3.6 | Preparation and publication of updated whitelist of pre-qualified TB manufacturers | [42 empty] | x | x | x | x | x | [6 empty] | Oct-Nov
1.3.7 | Coordination with QSM |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x | Jan-Dec
| 1.4 Coordination of GDF supply agents and monitoring agents | [55 empty] | Frequency of meetings with contractual agents | At least three face to face meetings with all contractual agents | GDF report | * Extension conditional on result of GDF evaluation
1.4.1. | Regular communication and video conferences with GDF contractual partners for supply and monitoring |  |  |  | x | [18 empty] | x | [16 empty] | x | [13 empty] | Jan, May, Sept
1.4.2 | Super Team' meetings between GDF secretariat and contractual partners for supply and monitoring |  |  |  | x | [18 empty] | x | [16 empty] | x | [13 empty] | Jan, May, Sept
1.4.3 | Contracts and extensions of contracts with GDF supply agents and monitoring agents | x | x | x | x | x | [22 empty] | x | x | x | x | x | x | [20 empty] | Jan and Jul
1.4.4 | Financial and technical reports from procurement agent and monitoring agents | x |  |  |  |  | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  |  | Jan-Dec
| 1.5 Grants of first line TB drugs for GDF | [55 empty] | Average lead time from placement of order to arrival of drugs at port of entry | 30 days | GDF database | Assumes 98% of orders supplied from GDF stock pile
1.5.1 | Issue tender |  |  |  |  | x | [48 empty] | Jan
1.5.2 | Adjudication of bids | [10 empty] | x | [42 empty] | Mar
1.5.3 | Selection and appointment of suppliers (split order) | [11 empty] | x | [41 empty] | Mar |  | No of manufacturers contracted to supply to GDF | Three manufacturers per product | Procurement agent report
1.5.4 | Establish stockpile(s) of GDF products | [15 empty] | x | [37 empty] | Apr
1.5.5 | Place orders with procurement agent | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
1.5.6 | Quality control and pre shipment inspection | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec |  | Proportion of batches passing external quality control | 100% | Reports from quality control agent
1.5.7 | Shipping/freight to countries | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
| 2.1 Global TB drug market survey | [55 empty] | Quantities, specifications and quality of TB drugs use in public and private sectors | Complete data from all high TB burden countries and major manufacturing countries | Global TB drug market survey report | * Assumes countries will submit timely, accurate and complete responses * Assumes private sector data available from IMS
2.1.1 | Modify drug market survey questionnaire | x | x | x | x | x | [48 empty] | Jan
2.1.2 | Identify contractual partner to conduct survey on behalf of GDF | x | x | x | x | x | x | x | x | x | x | [43 empty] | Jan-Mar
2.1.3 | Distribute survey and follow up with countries and regions | [10 empty] | x | x | x | x | x | x | x | [36 empty] | Mar-Apr
2.1.4 | Collect, screen and clean responses | [14 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [23 empty] | Apr-Jul
2.1.5 | Analyse responses | [22 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | [18 empty] | May-Aug
2.1.6 | Publish results | [40 empty] | x | [12 empty] | Sept
| 2.2 Product packaging development | [55 empty] | Proportion of GDF products supplied as blsiter packaged FDCs in patient boxes | At least 50% | GDF database | Assumes results of study (to be coordinated by TDR) will indicate the most effective form of packaging to simplify logistics, encourage rational use and promote adherence
2.2.1 | Operational research to collect an evidence base on the impact of various types of innovative packaging on drug logistics, rational use by health workers and patient compliance | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
2.2.2 | Reformulation and repackaging of 2 and 4 FDCs for use in intermittent regimens | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
| 3.1 GDF monitoring to ensure compliance with GDF terms and conditions | [55 empty] | Proportion of GDFsupported countries continuing to fulfill conditons of support | 100% | TRC recommendations | Assumes GDF monitoring visits will be integrated into monitoring of DOTS expansion by Stop TB partners
3.1.1 | Development of standardised assessment tool for DOTS monitoring, including GDF indicators | x | x | x | x | [49 empty] | Jan
3.1.2 | Database and planner of GDF monitoring missions | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
3.1.3 | Participate in monitoring missions to GDF supported countries | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
3.1.4 | Monitoring reports assessed by GDF desk audit agency | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
3.1.5 | Review by TRC of monitoring reports | [8 empty] | x | [20 empty] | x | [15 empty] | x | [7 empty] | Feb,Jul, Nov
3.1.6 | Grant agreements with countries for years 2 and 3 of support | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
| 4.1 Strengthened national TB drug management | [55 empty] | Proportion of GDF supported countries with drug management plan incorporated into DOTS expansion plan | 100% | GDF database | Effective use of drugs supplied by the GDF requires planning and monitoring of drug management
4.1.1 | Strategy developed in collaboration with DOTS expansion working group to promote in-country TB drug management |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | [38 empty] | Jan-Mar
4.1.2 | Facilitate incorporation of drug management plans into DOTS expansion plans | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
4.1.3 | Monitor implementation of TB drug management plans | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
4.1.4 | Develop collaborative plan with EDM to promote use of the GDF or FDC regimens by NTP programmes | [15 empty] | x | x | x | x | [34 empty] | Apr
4.1.5 | Establish and field test a TB drug flow critical path including all aspects of drug management, to be used by NTP control programmes for improving TB drug management |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [17 empty] | Jan-Aug
4.1.6 | Regional TB drug management meetings in at least four regions | [26 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jun-Dec
| 5.1 Pre-qualification of suppliers of diagnostics equipment and non-consumables | [55 empty] | Number of pre-qualified producers and manufacturers meeting GMP standards | At least 5 companies per product | Published Whitelist of Products and Manufacturers | * Adequate numbers of companies capable of producing products to meet GMP standards * Capacity of coordinators and inspectors to conduct document reviews and site inspections
5.1.1 | Determine specifications of diagnostics products to be supplied by GDF | x | x | x | x | x | x | x | x | x | [44 empty] | Jan-Feb
5.1.2 | Issue of General Procurement Notice inviting EOIs to supply TB diagnostics products | [9 empty] | x | [43 empty] | Mar
5.1.3 | Receipt of EOIs and issuance of Guidelines for Dossier Submission | [13 empty] | x | x | x | x | x | x | x | x | x | [31 empty] | Mar-May
5.1.4 | Receipt of completed product dossiers from interested suppliers and review of dossiers | [22 empty] | x | x | x | x | x | x | x | x | x | [22 empty] | May-July
5.1.5 | Arrangement and execution of GMP Physical site audits of eligible manufacturers | [27 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [5 empty] | Jul-Nov
5.1.6 | Preparation and publication of First Whitelist of pre-qualified manufacturers of TB diagnostics and non-consumables | [48 empty] | x | x | x | x | x | Dec
| 5.2 An expanded GDF catalogue to include products for the diagnosis of TB, and treatment of malaria and TB-HIV | [55 empty] | Numbers of products in GDF catalogue for TB diagnosis, and treatment of Malaria & TB-HIV | At least one additional product in each area | GDF database | Coordinating Board mandates GDF to expand scope and capacity.
5.2.1 | Complete risk assessment/feasibility study for expanded scope of the GDF | x | x | x | x | x | [48 empty] | Jan
5.2.2 | Identify products, specifications, sources, estimated supply needs and funding sources | [5 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [34 empty] | Feb-Apr
5.2.3 | Tender for products | [19 empty] | x | x | x | x | x | x | x | x | x | x | x | x | [22 empty] | May-July
5.2.4 | Procurement, quality control and supply | [31 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Aug-Dec
| 6.1 GDF Advocacy and Resource Mobilization | [55 empty] | GDF resources | 100% of funding required for 2003 available | GDF annual report | Assumes resources will flow through Stop TB Trust Fund, or directly to procurement agant from GFATM and other users of direct procurement mechanism
6.1.1 | Branding of GDF | x | x | x | x | x | [48 empty] | Jan
6.1.2 | Presentations on GDF to key stakeholders | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
6.1.3 | Publish GDF newsletter - 2 issues | [13 empty] | x | [25 empty] | x | [13 empty] | Mar and Sept
6.1.4 | GDF advocacy pack (fact sheets, CD, video) | [25 empty] | x | x | x | x | x | x | x | x | x | x | x | x | [16 empty] | Jun-Sept
6.1.5 | Enhancement of GDF website | x | x | x | x | x | [48 empty] | Jan
| 7.1 GDF internal management | [55 empty] | Implementation of GDF work plan | 100% achievement of GDF objectives and outputs within planned timeframes, budgeted resources and at predefined quality standards | GDF annual report
7.1.1 | Management of GDF resources, products and activities | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
7.1.2 | Preparation of annual workplans and budgets | [31 empty] | x | x | x | x | x | x | x | x | x | [13 empty] | Jul-Sep
7.1.3 | Semi-annual reports and interim financial reports on GDF progress and performance |  |  |  |  | x | x | x | x | [24 empty] | x | x | x | x | [17 empty] | Jan-Feb and Aug
7.1.4 | Information management | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
7.1.5 | Development of standard operating procedures for GDFactivities | x | x | x | x | x | [48 empty] | Jan
7.1.6 | Operational research to reduce lead time for GDF activites | x | x | x | x | x | x | x | x | x | [44 empty] | Jan-Feb

## ADV AND COMM
Stop TB Work Plan 2003
3 | Area of Work: ADVOCACY AND COMMUNICATIONS
| NARRATIVE | 2003 | [52 empty] | Timeline 2003 | Linkages | Indicators | Targets 2003 | Means of Verification | Assumptions & Risks
| Purpose | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
To build sustained international, regional and national support for the Global Plan to Stop TB
Objectives
| 1. Identify advocacy and communications priorities for the Stop TB Partnership at global and regional levels | [55 empty] | Development of cohesive and synergistic strategies for advocacy and communication | Creation of four regional focal points for TB advocacy and communications. | Meeting reports and strategy document
| 2. Plan, organize and coordinate advocacy & communications activities to support the global Stop TB mission | [55 empty] | Increased awareness of TB programme as well as case detection | Highlighting the role of TB patients in the control programme and 30% expansion of TB information recipients over 2002 levels | Country reports and independent evaluation reports
| 3. Develop mechanisms to address information needs of Stop TB Partners | [55 empty] | Streamlined mechanism for information sharing in place | Review mechanisms developed. Database and linkages developed | Products developed and implemented. Reports and materials
| 4. Develop mechanisms to provide advocacy & communications support at country level | [55 empty] | COMBI Plans developed and initiated | Complete and document 3 COMBI campaigns (Bangladesh, India and Kenya) | 3 reports on COMBI
| 5. Develop and implement partnership mechanisms to evaluate the effectiveness of advocacy & communications efforts | [55 empty] | A functional system for evaluation and documentation in place | Assesment tools, audiovisual software on Community Mobilization | Reports , best practises document, materials developed , audiovisual software
Products and Activities
| 1.1 Strategic guidance for advocacy and communications | [54 empty] | DEWG/RO/CO | Development of cohesive and synergistic strategies for advocacy and communication | Creation of four regional focal points for TB advocacy and communications. | Meeting reports and strategy document | Ongoing support for DOTS expansion in country and for communication & Advocacy. Lack of political will and shift of national priorities to other national programmes
1.1.1 | Meetings of the Stop TB Advocacy and Communications Group | [11 empty] | x | [13 empty] | x | [12 empty] | x | [11 empty] | x |  |  | Mar, Jun, Sept, Dec | 2.1.4
| 1.2 Media and political advocacy | [55 empty] | Increased media coverage and funding for global TB efforts | Creation of four regional focal points for TB advocacy and communications. | Meeting reports and strategy document
1.2.1 | Development and coordination of regional media networks | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
1.2.2 | Development and coordination of political advocacy networks | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec | RMD
| 2.1 World TB Day | [54 empty] | DEWG/ RO | Increased case detection and organized patient groups | Highlighting the role of TB patients in the control programme | Country reports | TB continues to be a national priority with political commitment. Shift in national priorites
2.1.1 | World TB 2003 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [39 empty] | Jan-Mar
2.1.2 | WTBD 2003 highlights report | [28 empty] | x | x | x | x | x | x | x | x | x | x | x | x | [13 empty] | Jul-Sept
2.1.3 | World TB Day 2004 planning and theme development preparation | [31 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Aug-Dec
2.1.4 | Preparation and distribution of WTBD 2004 materials | [31 empty] | xxx | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Aug-Dec
| 2.2 Public awareness and information dissemination | [55 empty] | Increased awareness about global TB programme | 30% expansion of TB information recipients over 2002 levels | Independent evaluation reports
2.2.1 | Production and distribution of the State of World's Effort to Stop TB | [35 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Sept-Dec
2.2.2 | Production and distribution of newsletters | [5 empty] | x | x | x | x | x | x | [11 empty] | x | x | x | x | x | x | x | [11 empty] | x | x | x | x | x | x | x | [6 empty] | Jan-Feb, June-Jul, Sept-Oct
2.2.3 | Production of ad hoc materials to support STB public events | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
2.2.4 | Analysis and dissemination of information | [16 empty] | x | x | [27 empty] | x | x | [6 empty] | Apr, Nov
2.2.5 | Continued development and promotion of STB image library | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
| 3.1 Information mechanism/IT support | [54 empty] | DEWG/RO | Streamlined mechanism for information sharing in place | Identify 3 major areas of imporvement on how information is managed | Analysis of feedback | Assumes buy-in from senior members of team to adopt a standard operating method
3.1.1 | Regular review /needs for information | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
3.1.2 | IT support to database development and linkages | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
3.1.3 | Website software and server hosting | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
3.1.4 | Informationa systems/products | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
3.1.5 | Partners database maintenance and strengthening | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
| 4.1 Community mobilization to support DOTS expansion | [54 empty] | DEWG/RO/CO/SMT/NTP | COMBI Plans developed and initiated | Complete and document 3 COMBI campaigns | 3 reports on COMBI | Continued country support and capacity to implement. Lack of country capacity and personnel.
4.1.1 | Complete monitoring and evaluation of 3 COMBI plans in 3 initial HBCs |  | xXx | x | x | x | x | x | x | x | x | x | x | xx | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | xx | x | x | x | x | x | x | Jan-Dec
4.1.2 | Develop COMBI best practices for ROs and NTPs | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [35 empty] | Jan-Apr | 5.1.1
4.1.3 | Develop and implement COMBI training courses and promote COMBI in high burden countries | [18 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [7 empty] | May-Oct
4.1.4 | Production, duplication and distribution of documentary film in Bangladesh | [17 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [20 empty] | Apr-Aug
4.1.5 | Production of booklet on COMBI | [17 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [20 empty] | Apr-Aug | 4.1.2
4.1.6 | Participate in DEWG country missions | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
| 5.1 Evaluation, assessment and documentation | [54 empty] | DEWG/SMT/RO | A functional system for evaluation and documentation in place | Assesment tools, audiovisual software on Community Mobilization | Reports , best practises document, materials developed , audiovisual software | Country and partner support for documentation , Availability of professionals.Delay and non completion of projects
5.1.1 | Development of communications & advocacy assessment tools for NTPs | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [39 empty] | Jan-Mar | 4.1.2
5.1.2 | Review of Countdown campaign in 2003 | [25 empty] | x | x | x | x | x | [23 empty] | Jun-Jul | 2.1.1
5.1.3 | Duplication and distribution of documentary film in Eastern Europe to ROs and NTPs | [5 empty] | x | x | x | x | x | x | x | x | [40 empty] | Jan-Feb

## ADMINISTRATION
Stop TB Work Plan 2003
4 | Area of Work: Administration
| NARRATIVE | 2003
| Purpose | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Timeline 2003 | Linkages | Indicators | Targets 2003 | Means of Verification | Assumptions & Risks
To support Stop TB Partners in the fulfilment of the vision and mission of the global partnership
Objectives
| 1. To facilitate the management of the Global Partnership through the support of its governing structures | [55 empty] | Timely reports and follow-up action | Successful coordinating board and partners' forum meetings | Meeting reports, Partnership evaluation reports and monitoring tools for administration and management | Partnership Secretariat in terms of identity is fragile and does not have a legal personality. Thus it is difficult to fully operate without the sanction of the host institution.
| 1.1 Administrative and logistical management of the partnership | [54 empty] | All areas of work | Timely reports and follow-up action | Successful coordinating board and partners' forum meetings | Meeting reports, Partnership evaluation reports and monitoring tools for administration and management | Partnership Secretariat in terms of identity is fragile and does not have a legal personality. Thus it is difficult to fully operate without the sanction of the host institution.
1.1.1 | Support and maangement of staff in the secretariat |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
1.1.2 | Provision of office space and office equipment |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Jan-Dec
1.1.3 | Monitoring of finances, budget and cash flows | xx | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | xx | x | x | x | x | x | x | x | x | x | x | Jan-Dec
1.1.4 | Capacity and team building | [23 empty] | x | x | x | x | [22 empty] | x | x | x |  | Jun and Dec

## ANNEX 1
Stop TB Work Plan 2003
1 | Area of Work: Partnership
| NARRATIVE | 2003
| Products and Activities | [14 empty] | Linkages | Indicators | Targets 2003 | Means of Verification | Assumptions & Risks | TBP responsible | Component | FTE (P) | FTE(G) | No./Units | Unit cost | Staff cost | Cost of Activities | Contribution in kind | Implementors
| Objective 6: To increase the flow of resources in support of reaching the Global Plan targets | [15 empty] | Funding Gap | 25% additional resources available for Global plan | Resource Mobilization Directory
| 1.1 Enhance performance of global partners | [19 empty] | PH | Staff time
[22 empty] | P-staff | 78 |  |  | 120000 | 105768
[22 empty] | G-staff |  | 48 |  | 60000 | 32544
1.1.1 | Coordinating Board Meetings and teleconferences held at regular intervals through support of the Secretariat | [15 empty] | Number of board meetings and teleconferences |  | Meeting reports |  | PH/JK/IS/GS/ML/LA
| (a) Coordinating Board Meeting - February and October 2003 | [20 empty] | Meeting | 24 | 16 | 2 | 50000 |  | 113000
| (b) Working Committee teleconference - once a month | [20 empty] | Tel. costs and staff time | 12 | 4 | 10 | 1000 |  | 11300
| (c) Board teleconferences - every quarter | [20 empty] | Tel. costs and staff time | 6 | 2 | 4 | 1000 |  | 4520
1.1.2 | Evaluation of the Global Partnership to Stop TB | [15 empty] | Internal Evaluation Review |  | Evaluation Report |  | PH/JKIS/GS/ML/LA | Staff time | 12 | 2
| (a) External reviewers fee | [20 empty] | APW |  |  | 1 | 250000 |  | 282500
1.1.3 | Stop TB Partners Forum, 2003 | [15 empty] | Number of active participating partners |  | Meeting report |  | PH/JK/IS/GS/ML/LA | Staff time | 24 | 24
| (a) Preparatory meeting and Partners Forum, November 2003 | [20 empty] | Meeting |  |  | 1 | 500000 |  | 565000
| Sub-total | [25 empty] | 138312 | 976320
| 2.1 Functional expanded regional partnerships | [15 empty] | Number of Working Partnerships | 6 regional partnerships | Semi-annual reports |  | GS | Staff time
[22 empty] | P-staff | 40 |  |  | 120000 | 54240
[22 empty] | G-staff |  | 14 |  | 60000 | 9492
2.1.1 | Regional partnership IT support for establishing directories | [19 empty] | YP/SR | Staff time | 12 | 2
| (a) Visit to Regions - AFRO/AMRO/EURO/SEARO | [20 empty] | Duty travel |  |  | 4 | 2500 |  | 11300
2.1.2 | Regional meetings to engage more partners | [14 empty] | 5.3 |  |  |  |  | PH/DA | Staff time | 16 | 8
| (a) Regional meetings - AFRO/AMRO/EURO/SEARO | [20 empty] | Meetings |  |  | 4 | 50000 |  | 226000
2.1.3 | Building regional partnership | [14 empty] | 5.3 |  |  |  |  | GS/PH | Staff time | 12 | 6
| (a) Missions to support Regions | [20 empty] | Duty travel |  |  | 4 | 2500 |  | 11300
| Sub-total | [25 empty] | 63732 | 248600
| 2.2 Functional expanded national partnerships in all 22 HBC | [15 empty] | # Working Partnerships | 22 HBC partnerships and 6 partnerships in other countries | Semi-annual reports | The commitment to DOTS Expansion is the basic assumption.The capabilities to run a partnership secretariat are assumed. The lack of partners' participation is a potential risk, also communicative skills of the partnership facilitator at the secretariat. | GS | Staff time
[22 empty] | P-staff | 44 |  |  | 120000 | 59664
[22 empty] | G-staff |  | 8 |  | 60000 | 5424
2.2.1 | Pilot national partnerships IT and logistical support | [19 empty] | YP/PH | Staff time | 4 | 2
| (a) Country missions | [20 empty] | Duty travel |  |  | 2 | 2500 |  | 5650
2.2.2 | National meetings in 22 HBC to engage more partners on the Expanded Framework for DOTS Expansion | [19 empty] | GS/DA | Staff time | 20 | 4
| (a) Support to national meetings (10 countries) | [20 empty] | Meetings |  |  | 10 | 5000 |  | 56500
2.2.3 | Strengthen the NICC/CCM through country visits | [14 empty] | 5.3 |  |  |  |  | GS/ML/PH | Staff time | 20 | 4
| (a) Country missions | [20 empty] | Duty travel |  |  | 10 | 2500 |  | 28250
| Sub-total | [25 empty] | 65088 | 90400
| 3.1 Joint outputs of all Working Groups in support of reaching the Global Plan 2005 targets | [15 empty] | # Joint activities | Each WG has at least 2 joint activities with other WGs | Semi-annual reports | Willingness to work together is assumed and commitment to global Plan a requirement. The risks are mainly in the field of joint activities, when credits for work/output and funding are underlying issues. | PhH | Staff time
[22 empty] | P-staff | 34 |  |  | 120000 | 46104
[22 empty] | G-staff |  | 8 |  | 60000 | 5424
3.1.1 | Support to monitoring of WG's progress and output | [19 empty] | PhH, GS | Staff time | 8 | 2
| (a) Monitoring missions | [20 empty] | Duty travel |  |  | 2 | 2500 |  | 5650
3.1.2 | Annual Joint Meetings for all WG chairs and secretariats to harmonise and focus respective agendas | [19 empty] | PhH, GS | Staff time | 8 | 4
| (a) Working Group meeting, June 2003 | [20 empty] | Meeting |  |  | 1 | 30000 |  | 33900
3.1.3 | Linking Research WG activities with country based DOTS Expansion | [19 empty] | PhH, GS | Staff time | 18 | 2
| (a) Country missions | [20 empty] | Duty travel |  |  | 5 | 2500 |  | 14125
| Sub-total | [25 empty] | 51528 | 53675
| 4.1 Contributions of current and new partners are in line with the reaching of the 2005 Global Plan targets | [15 empty] | # Active Partners | 90% of partners' contributions can be directly related to reaching the 2005 Global Targets | Partners Directory | The willingness and ability of partners to contribute is assumed. The risk is the willingness by partners to accept Partnership suggestions for funding or support. | PH | Staff time
[22 empty] | P-staff | 62 |  |  | 120000 | 84072
[22 empty] | G-staff |  | 20 |  | 60000 | 13560
4.1.1 | Mobilize partners through partners directory | [19 empty] | PH/JK/DA | Staff time | 18 | 6
| (a) Visits to partners | [20 empty] | Duty travel |  |  | 6 | 2500 |  | 16950
4.1.2 | Publish annual overview of partners financial contributions | [19 empty] | LA/DA | Staff time | 16 | 8
| (a) Cost of writing and publication of reports | [20 empty] | APW |  |  | 1 | 10000 |  | 11300
4.1.3 | Develop close working relationship with other global initiatives and partnerships (including the GFATM) | [19 empty] | JK/IS | Staff time | 10 | 2
4.1.4 | Information package for donors and other agencies on reaching the global targets, including corporate sector | [19 empty] | DA/ML/SE/LA | Staff time | 8 | 2
| (a) Production of package materials | [20 empty] | APW |  |  | 1 | 10000 |  | 11300
4.1.5 | Negotiate strategic alignments with donors to synergise inputs | [19 empty] | JK/GS/SE | Staff time | 10 | 2
| Sub-total | [25 empty] | 97632 | 39550
| 5.1 Annual Status Report on the progress of the Global Plan to Stop TB | [15 empty] | 2003 State of World TB Epidemic Report | Report published in time for WTB 2003 | Publication & Partners Forum | The timely availability of the input data and the related clearance by WH and CB are assumed. The risks are the contractual writers and the consensus among CB members on the final contens | SE | Staff time
[22 empty] | P-staff | 32 |  |  | 120000 | 43392
[22 empty] | G-staff |  | 10 |  | 60000 | 6780
5.1.1 | Production of the TB and Poverty booklet as input to the State of the World's Effort to Stop TB, 2003 | [19 empty] | GS/SE | Staff time | 8 | 2
| (a) Production cost | [20 empty] | APW |  |  | 1 | 20000 |  | 22600
5.1.2 | Writing and preparation of technical contents of the State of the World's Effort to Stop TB, 2004 and engaging partners to submit contributions to the report | [19 empty] | SE/GS/ML | Staff time | 24 | 8
| (a) Writing for sections of the report | [20 empty] | APW |  |  | 1 | 10000 |  | 11300
| Sub-total | [25 empty] | 50172 | 33900
Sub-Total
| 6.1 Increase of resource flow to meet the Global Plan targets | [15 empty] | Funding Gap | Funding gap of high-priority components reduced by 50% | Resource Mobilization Directory | Assumptions: Political commitment among donoragencies and contributing partners to make additional resources available. The continued political commitment from all partners and donor agencies to continue their previously declared support for the Amsterdam | DA | Staff time
[22 empty] | P-staff | 96 |  |  | 120000 | 130176
[22 empty] | G-staff |  | 20 |  | 60000 | 13560
6.1.1 | Increase the advocacy and resource mobilization activities in meeting the funding gap requirements | X | X | X | X | X | [10 empty] | Increase in project input into RMD for funding support. |  | Newsreleases,Newsletters with links and references to the RMD placed on STB website,Periodicals |  | DA/ML/PH/SE/LA | Staff time | 40 | 8
| (a) Visits to current and prospective donors | [20 empty] | Duty travel |  |  | 6 | 2500 |  | 16950
6.1.2 | Facilitating the implementation of the Resource Mobilization (RM) guidelines both at Regional and National levels through WEF | [15 empty] | RM meetings and workshops held |  | Report on RM workshops submitted |  | DA/GS/PH/SE | Staff time | 8 | 2
| (a) Producing RM guidelines | [20 empty] | APW |  |  | 1 | 5000 |  | 5650
6.1.3 | Inviting more partners at Regional Level meetings dealing on Resource Mobilization | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  | i) Report of workshop/meetings submitted ii) Letter of interest for projects fundign received from donors |  | DA/SE/LA | Staff time | 12 | 4
6.1.4 | Resource Mobilization Directory contact booklet developed and updated regularly per region | [14 empty] | 1.2 | i)List of in-kin support need completed. Ii) Identification and screening of possible corporate andprivate sector donors. iii) Mapping of existing collaboration iv) donor contact sheet updated regularly |  | I) Donor contributions increased by 25% ii) Scale up of involved of donors. Iii) Increase in APO'S AND SECONDMENTS iv) Donor contact booklet launched. |  | DA/YP/SE | Staff time | 12 | 2
6.1.5 | Countries needs determined for STB support/information in line with their resource mobilization efforts. | [14 empty] | 3.2, 3.6 | Plan developed and needs elaborated for support |  | Newly identified projects inputted into RMD |  | DA/SE/LA | Staff time | 12 | 2
6.1.6 | Facilitating financing of partnership and working groups activites through various channels | [19 empty] | SE/LA | Staff time | 12 | 2
| (a) Visit and meet with various collaborating institutions | [20 empty] | Duty travel |  |  | 3 | 2500 |  | 8475
| Sub-total | [25 empty] | 143736 | 31075
| Sub-total for Staff cost and Cost of Activities | [20 empty] | Total FTEs 6.4 | 386 | 128 |  |  | 610200 | 1473520
| Total for Staff cost and Activities for Partnership | [26 empty] | 2083720
Grand Total

## ANNEX 2
Stop TB Work Plan 2003
2 | Area of Work: Global TB Drug Facility
| Products and Activities | TBP Responsible | Components | FTE(P) | FTE(G) | No./Unit | Unit Cost | Staff Cost | Cost of Activities | Contributions in kind | Implementors
| 1.1 Demand assessment and demand creation for GDF services (grants and direct procurement) | VA | Staff time
|  |  | P-staff | 34 |  |  | 120000 | 46104
|  |  | G-staff |  | 13 |  | 60000 | 8814
1.1.1 | Assess demand for first line TB drugs and resource gaps in GDF priority countries | VA | Staff time | 4 | 2
| (a) Contract for demand assessment |  | APW |  |  | 1 | 5000 |  | 5650
1.1.2 | Establish procedures for use of Direct Procurement by international agencies including GFATM, World Bank, regional banks and other major donors | IS | Staff time | 12 | 2
| (a) Visits to other agencies |  | Duty travel |  |  | 2 | 2500 |  | 5650
1.1.3 | Coordinate applications with GFATM secretariat | VA | Staff time | 4 | 1 |  |  |  | 0
1.1.4 | Assess demand for diagnostics | VA | Staff time | 4 | 4
| (a) Contract for demand assessment |  | APW |  |  | 1 | 50000 |  | 56500
1.1.5 | Invite applications to GDF grants for first line TB drugs and diagnostics, and for direct procurement | VA/AV/LM | Staff time | 4 | 2 |  |  |  | 0
1.1.6 | Assess demand for second line drugs in collaboration with GLC | VA | Staff time | 2 | 0 |  |  |  | 0
1.1.7 | Collaborate with GLC in applications and review for second line drugs | IS/VA | Staff time | 4 | 2 |  |  |  | 0
| Sub-total | [6 empty] | 54918 | 67800
| 1.2 Application and review process for GDF grants | VA | Staff time
|  |  | P-staff | 74 |  |  | 120000 | 100344
|  |  | G-staff |  | 50 |  | 60000 | 33900
1.2.1 | Accept applications for first line TB drugs (and diagnostics) and applications for direct procurement | VA/RM/LM/AV | Staff time | 2 | 2
1.2.2 | Screening of applications for grants and direct procurement | VA/AV/RM/LM | Staff time | 12 | 6
1.2.3 | Review of grant applications by GDF technical review committee | VA/AV | Staff time | 16 | 16
| (a) Technical Review Committee meetings |  | Meetings |  |  | 3 | 30000 |  | 101700
1.2.4 | Country visits | VA/RM/IS/JK/TM/HV | Staff time | 24 | 8 |  |  |  |  | Partners' staff
| (a) Visits to approved countries |  | Duty travel |  |  | 10 | 2500 |  | 28250
1.2.5 | Grant agreements | VA/LM/AV | Staff time | 16 | 16
1.2.6 | Develop application mechanism for TB diagnostics | VA | Staff time | 4 | 2
| (a) Contract for the development of application mechanism |  | APW |  |  | 1 | 5000 |  | 5650
| Sub-total | [6 empty] | 134244 | 129950
| 1.3 Whitelist of pre-qualified manufacturers of quality TB products | HV | Staff time
|  |  | P-staff | 16 |  |  | 120000 | 21696
|  |  | G-staff |  | 14 |  | 60000 | 9492
1.3.1 | Publication of first whitelist of pre-qualified TB manufacturers through 2001 GDF-EDM/QSM project | RM | Staff time | 2 | 2 | [5 empty] | TBP/EDM
1.3.2 | Issue second General Procurement Notice inviting expressions of interest (EOI) to supply TB products | HV/RM | Staff time | 2 | 0 | [5 empty] | TBP/EDM
1.3.3 | Receipt of EOIs and issuance of Guidelines for Dossier Submission by EDM/QSM | HV/RM | Staff time | 2 | 0 | [5 empty] | EDM/QSM
1.3.4 | Review of product dossiers from suppliers by EDM/QSM | HV/RM | Staff time | 2 | 6 |  |  |  |  | 2 EDM staff (P&G) | EDM/QSM
1.3.5 | GMP physical site audits of eligible manufacturers | HV/RM | Staff time | 2 | 2 |  |  |  |  | 1 EDM staff | EDM/QSM
1.3.6 | Preparation and publication of updated whitelist of pre-qualified TB manufacturers | RM |  | 2 | 2 | [5 empty] | TBP/EDM
1.3.7 | Coordination with QSM | RM |  | 4 | 2 |  |  |  | 0
| (a) Advertisements |  | APW |  |  | 10 | 1000 |  | 11300
| (b) MOU with EDM/QSM |  | APW |  |  | 1 | 100000 |  | 113000
| (c) MOU with EDM/QSM for execution of physical audits |  | APW |  |  | 1 | 200000 |  | 226000
| Sub-total | [6 empty] | 31188 | 350300
| 1.4 Coordination of GDF supply agents and monitoring agents | RM | Staff time
|  |  | P-staff | 42 |  |  | 120000 | 56952
|  |  | G-staff |  | 8 |  | 60000 | 5424
1.4.1 | Regular communication and video conferences with GDF contractual partners for supply and monitoring | RM | Staff time | 16 | 2
| (a) Videoconferences |  | Tel. Costs |  |  | 10 | 200 |  | 2260
1.4.2 | Super Team' meetings between GDF secretariat and contractual partners for supply and monitoring | RM | Staff time | 10 | 2
| (a) Participation to meetings |  | Duty travel |  |  | 15 | 2500 |  | 42375
1.4.3 | Contracts and extensions of contracts with GDF supply agents and monitoring agents | HV/RM | Staff time | 12 | 2 |  |  |  |  | 1%
| (a) Contractual fees for procurement (1%) of cost of drugs, quality control and pre-shipment inspection and cost of insurance, shipping and freight to countries |  | APW |  |  | 1 | 374400 |  | 423072
1.4.4 | Financial and technical reports from procurement agent and monitoring agents | VA/RM/LA | Staff time | 4 | 2
| Sub-total | [6 empty] | 62376 | 467707
| 1.5 Grants of first line TB drugs for GDF | HV/RM | Staff time
|  |  | P-staff | 28 |  |  | 120000 | 37968
|  |  | G-staff |  | 20 |  | 60000 | 13560
1.5.1 | Issue tender | HV | Staff time | 4 | 4 | [5 empty] | Proc agent
1.5.2 | Adjudication of bids | HV | Staff time | 2 | 2 | [5 empty] | Proc agent
| (a) Contract for members to adjudicate committee |  | APW |  |  | 1 | 15000 |  | 16950
1.5.3 | Selection and appointment of suppliers (split order) | HV | Staff time | 4 | 2 | [5 empty] | Proc agent
| (a) Visit to suppliers |  | Duty travel |  |  | 2 | 2500 |  | 5650
1.5.4 | Establish stockpile(s) of GDF products | HV/RM | Staff time | 8 | 2 | [5 empty] | TBP and suppliers
1.5.5 | Place orders with procurement agent | RM | Staff time | 4 | 4 |  |  |  |  | grants and direct | Proc agent
| (a) Cost of drugs (to be coordinated with Global Funds for AIDS, TB and Malaria -GFATM) |  | Drugs |  |  | 1 | 32000000 |  | 33920000
| (b) Sub-contract for quality control and pre-shipment inspection |  | APW |  |  | 1 | 1280000 |  | 1446400
| (c) Cost for insurance, shipping and freight to countries |  | APW |  |  | 1 | 4160000 |  | 4700800
1.5.6 | Quality control and pre shipment inspection | RM | Staff time | 4 | 4 |  |  |  |  | 4% | Proc agent
1.5.7 | Shipping/freight to countries | RM | Staff time | 2 | 2 |  |  |  |  | 13% | Proc agent
| Sub-total | [6 empty] | 176280 | 40089800
| 2.1 Global TB drug market survey | TM | Staff time
|  |  | P-staff | 14 |  |  | 120000 | 18984
|  |  | G-staff |  | 10 |  | 60000 | 6780
2.1.1 | Modify drug market survey questionnaire | TM | Staff time | 2 | 1
2.1.2 | Identify contractual partner to conduct survey on behalf of GDF | TM | Staff time | 4 | 2
| (a) Contract for the survey |  | APW |  |  | 1 | 50000 |  | 56500
2.1.3 | Distribute survey and follow up with countries and regions | Partner | Staff time | 2 | 1
2.1.4 | Collect, screen and clean responses | Partner | Staff time | 2 | 1
2.1.5 | Analyse responses | Partner | Staff time | 2 | 1
2.1.6 | Publish results | TM | Staff time | 2 | 4
| (a) Cost of publication |  | APW |  |  | 1 | 5000 |  | 5650
| Sub-total | [6 empty] | 25764 | 62150
| 2.2 Product packaging development | TM | Staff time
| (Activity cost by TDR) |  | P-staff | 16 |  |  | 120000 | 21696
|  |  | G-staff |  | 8 |  | 60000 | 5424
2.2.1 | Operational research to collect an evidence base on the impact of various types of innovative packaging on drug logistics, rational use by health workers and patient compliance | TM | Staff time | 8 | 4 | [5 empty] | TDR
2.2.2 | Reformulation and repackaging of 2 and 4 FDCs for use in intermittent regimens | TM | Staff time | 8 | 4 | [5 empty] | TDR
| Sub-total | [6 empty] | 27120 | 0
| 3.1 GDF monitoring to ensure compliance with GDF terms and conditions | TO | Staff time
|  |  | P-staff | 76 |  |  | 120000 | 103056
|  |  | G-staff |  | 27 |  | 60000 | 18306
3.1.1 | Development of standardised assessment tool for DOTS monitoring, including GDF indicators | TO/VA/RM | Staff time | 4 | 1 | [5 empty] | TBP
3.1.2 | Database and planner of GDF monitoring missions | TO/AV/YP | Staff time | 12 | 2
3.1.3 | Participate in monitoring missions to GDF supported countries | TO/VA/RM/TM/IS/HV | Staff time | 28 | 8 | [5 empty] | Partners
| (a) Monitoring missions to countries |  | Duty travel |  |  | 12 | 2500 |  | 33900
3.1.4 | Monitoring reports assessed by GDF desk audit agency | TO | Staff time | 12 | 4 | [5 empty] | Desk auditors
| (a) Contracts with audit agencies |  | APW |  |  | 1 | 20000 |  | 22600
3.1.5 | Review by TRC of monitoring reports | VA/TO |  | 4 | 4 | [5 empty] | TRC
3.1.6 | Grant agreements with countries for years 2 and 3 of support | VA/TO/RM | Staff time | 16 | 8
| Sub-total | [6 empty] | 121362 | 56500
| 4.1 Strengthened national TB drug management | TM | Staff time
|  |  | P-staff | 44 |  |  | 120000 | 59664
|  |  | G-staff |  | 8 |  | 60000 | 5424
4.1.1 | Strategy developed in collaboration with DOTS expansion working group to promote in-country TB drug management | TM | Staff time | 4 | 1 | [5 empty] | DEWG
4.1.2 | Facilitate incorporation of drug management plans into DOTS expansion plans | TM | Staff time | 8 | 2
4.1.3 | Monitor implementation of TB drug management plans | TM/VA | Staff time | 16 | 2
| (a) Visits to countries |  | Duty travel |  |  | 6 | 2500 |  | 16950
4.1.4 | Develop collaborative plan with EDM to promote use of the GDF or FDC regimens by NTP programmes | TM | Staff time | 4 | 1
4.1.5 | Establish and field test a TB drug flow critical path including all aspects of drug management, to be used by NTP control programmes for improving TB drug management | TM | Staff time | 4 | 0 | [5 empty] | Lausanne University
4.1.6 | Regional TB drug management meetings in at least four regions | TM | Staff time | 8 | 2
| (a) Support to organisations of meetings |  | Duty travel |  |  | 2 | 2500 |  | 5650
| Sub-total | [6 empty] | 65088 | 22600
| 5.1 Pre-qualification of suppliers of diagnostics equipment and non-consumables | HV | Staff time
| (Cost of diagnostics not budgetted) |  | P-staff | 16 |  |  | 120000 | 21696
|  |  | G-staff |  | 8 |  | 60000 | 5424
5.1.1 | Determine specifications of diagnostics products to be supplied by GDF | HV | Staff time | 6 | 1 | [5 empty] | TBP
| (a) Contracts for specification documents |  | APW |  |  | 1 | 5000 |  | 5650
5.1.2 | Issue of General Procurement Notice inviting EOIs to supply TB diagnostics products | HV/RM | Staff time | 2 | 0 | 10 |  |  |  |  | TBP
| (a) Advertisements |  | APW |  |  | 10 | 1000 |  | 11300
5.1.3 | Receipt of EOIs and issuance of Guidelines for Dossier Submission | HV/RM | Staff time | 2 | 1
5.1.4 | Receipt of completed product dossiers from interested suppliers and review of dossiers | HV/RM | Staff time | 2 | 2
5.1.5 | Arrangement and execution of GMP Physical site audits of eligible manufacturers | HV/RM | Staff time | 2 | 2
| (a) Contract for site audits |  | APW |  |  | 1 | 100000 |  | 113000
5.1.6 | Preparation and publication of First Whitelist of pre-qualified manufacturers of TB diagnostics and non-consumables | RM | Staff time | 2 | 2 |  |  |  | 0
| Sub-total | [6 empty] | 27120 | 129950
| 5.2 An expanded GDF catalogue to include products for the diagnosis of TB, and treatment of malaria and TB-HIV | IS | Staff time
| (Cost of products not budgetted) |  | P-staff | 32 |  |  | 120000 | 43392
|  |  | G-staff |  | 13 |  | 60000 | 8814
5.2.1 | Complete risk assessment/feasibility study for expanded scope of the GDF | IS | Staff time | 2 | 1
5.2.2 | Identify products, specifications, sources, estimated supply needs and funding sources | IS/HV/TM | Staff time | 6 | 2
5.2.3 | Tender for products | HV | Staff time | 8 | 2
5.2.4 | Procurement, quality control and supply | HV/RM | Staff time | 16 | 8
| Sub-total | [6 empty] | 52206 | 0
| 6.1 GDF Advocacy and Resource Mobilization | IS | Staff time
|  |  | P-staff | 28 |  |  | 120000 | 37968
|  |  | G-staff |  | 12 |  | 60000 | 8136
6.1.1 | Branding of GDF | VA/IS/RM/ML | Staff time | 4 | 2
| (a) Contract for development of branding concept |  | APW |  |  | 1 | 10000 |  | 11300
6.1.2 | Presentations on GDF to key stakeholders | IS/GDF | Staff time | 12 | 2
| (a) Visit to partners |  | Duty travel |  |  | 12 | 2500 |  | 33900
6.1.3 | Publish GDF newsletter - 2 issues | VA/ML | Staff time | 4 | 4
| (a) Cost of printing of 2 issues |  | APW |  |  | 2 | 10000 |  | 22600
6.1.4 | GDF advocacy pack (fact sheets, CD, video) | IS/ML | Staff time | 4 | 2
| (a) Cost of developmetn and publication |  | APW |  |  | 1 | 30000 |  | 33900
6.1.5 | Enhancement of GDF website | IS | Staff time | 4 | 2
| (a) Contract for enhancement |  | APW |  |  | 1 | 10000 |  | 11300
| Sub-total | [6 empty] | 46104 | 113000
| 7.1 GDF internal management | IS | Staff time
|  |  | P-staff | 120 |  |  | 120000 | 162720
|  |  | G-staff |  | 30 |  | 60000 | 20340
7.1.1 | Management of GDF resources, products and activities | IS/LA | Staff time | 80 | 12
7.1.2 | Preparation of annual workplans and budgets | IS/LA | Staff time | 8 | 2
7.1.3 | Semi-annual reports and interim financial reports on GDF progress and performance | IS | Staff time | 12 | 4
7.1.4 | Information management | GDF | Staff time | 8 | 8
7.1.5 | Development of standard operating procedures for GDFactivities | VA/RM/IS | Staff time | 12 | 4
7.1.6 | Operational research to reduce lead time for GDF activites | IS | Staff time | 4 | 2
| Sub-total | [6 empty] | 183060 | 0
| Sub-total for Staff Cost and Activities for Global TB Drug Facility |  | FTEs 9.7 | 540 | 233 |  |  | 1006830 | 41489757
| Total cost for Global TB Drug Facility 2003 Workplan | [7 empty] | 42496587

## ANNEX 3
Stop TB Work Plan 2003
3 | Area of Work: ADVOCACY AND COMMUNICATIONS
|  | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Linkages | TBP responsible | Component | FTE (P) | FTE (G) | No./Unit | Unit cost | Staff Cost | Cost of Activities | Contributions in kind | Implementors
Products and Activities
| 1.1 Strategic guidance for advocacy and communications | [12 empty] | DEWG/RO/CO | ML | Staff time
[16 empty] | P-staff | 12 |  |  | 120000 | 16272
[16 empty] | G-staff |  | 16 |  | 60000 | 10848
1.1.1 | Meetings of the Stop TB Advocacy and Communications Group | [13 empty] | ML, NV,PH | Staff time | 12 | 16
| (a) Annual meeting of the Stop TB Advocacy and Communications Group | [14 empty] | Meeting |  |  | 1 | 40000 |  | 45200
| (b) World TB Day 2003 Meeting | [14 empty] | Meeting |  |  | 1 | 30000 |  | 33900
| (c) Semi-annual meeting of the Stop TB Advocacy and Communications Group | [14 empty] | Meeting |  |  | 2 | 30000 |  | 67800
| Sub-total | [19 empty] | 27120 | 146900
| 1.2 Media and political advocacy | [13 empty] | ML | Staff time
[16 empty] | P-staff | 30 |  |  | 120000 | 40680
[16 empty] | G-staff |  | 10 |  | 60000 | 6780
1.2.1 | Development and coordination of regional media networks | [13 empty] | ML, NV, PH | Staff time | 18 | 8
| (a) Professional fees for regional public relations specialists | [14 empty] | APW |  |  | 4 | 50000 |  | 226000
| (b) Organization of press conferences, medial briefings, regional meetings, placement of media articles, promotion of TB events | [14 empty] | APW |  |  | 10 | 10000 |  | 113000
1.2.2 | Development and coordination of political advocacy networks | [12 empty] | RMB | ML, NV, PH | Staff time | 12 | 2
| (a) Organizations to support to briefings to parliamentarians, policy makers, opinion formers and facilitation of country visits by the same to high-burden countries (Results International and other partners) | [13 empty] | ML, NV, PH | APW |  |  | 4 | 25000 |  | 113000
| Sub-total | [19 empty] | 47460 | 452000
| 2.1 World TB Day | [12 empty] | DEWG/ RO | NV | Staff time
[16 empty] | P-staff | 26 |  |  | 120000 | 35256
[16 empty] | G-staff |  | 14 |  | 60000 | 9492
2.1.1 | World TB Day 2003 | [13 empty] | NV, ML, PH | Staff time | 6 | 2
| (a) Preparation of materials | [14 empty] | APW |  |  | 1 | 50000 |  | 56500
| (b) Preparation of events | [14 empty] | APW |  |  | 1 | 50000 |  | 56500
2.1.2 | WTBD 2003 highlights report | [13 empty] | NV, ML | Staff time | 6 | 4
| (a) Distribution costs | [14 empty] | APW |  |  | 1 | 5000 |  | 5650
2.1.3 | World TB Day 2004 planning and theme development preparation | [13 empty] | NV, ML, PH | Staff time | 14 | 8
| (a) Writing, layout design, production and distribution | [14 empty] | APW |  |  | 1 | 50000 |  | 56500
| Sub-total | [19 empty] | 44748 | 175150
| 2.2 Public awareness and information dissemination | [13 empty] | ML | Staff time
[16 empty] | P-staff | 14 |  |  | 120000 | 18984
[16 empty] | G-staff |  | 11 |  | 60000 | 7458
2.2.1 | Production and distribution of the State of World's Effort to Stop TB | [13 empty] | ML, NV, PH | Staff time | 4 | 6
| (a) Printing and distribution of the State of the World's Effort to Stop TB 2003 | [14 empty] | APW |  |  | 1 | 30000 |  | 33900
| (b) Preparation for the 2004 State of the World's Effort to Stop TB - writing and layout | [14 empty] | APW |  |  | 1 | 25000 |  | 28250
2.2.2 | Production and distribution of newsletters | [13 empty] | ML, PH | Staff time | 2 | 2
| (a) Writing, layout and distribution of newsletters | [14 empty] | APW |  |  | 3 | 10000 |  | 33900
2.2.3 | Production of ad hoc materials to support STB public events | [13 empty] | ML, PH | Staff time | 2 | 2
| (a) Contract for writing and layout (including GDF materials) | [14 empty] | APW |  |  | 1 | 20000 |  | 22600
2.2.4 | Analysis and dissemination of information | [13 empty] | YP | Staff time | 4 | 1
| (a) Contract work for the analysis and dissemination | [17 empty] | 1 | 10000 |  | 11300
2.2.5 | Continued development and promotion of STB image library | [13 empty] | ML | Staff time | 2 | [6 empty] | IUATLD
| (a) Commissioning photo work and support for IUATLD | [14 empty] | APW |  |  | 1 | 25000 |  | 28250
| Sub-total | [19 empty] | 26442 | 158200
| 3.1 Information mechanism/IT support | [12 empty] | DEWG/RO | YP | Staff time
[16 empty] | P-staff | 122 |  |  | 120000 | 165432
[16 empty] | G-staff |  | 142 |  | 60000 | 96276
3.1.1 | Regular review /needs for information | [13 empty] | YP/ML | staff time | 24 | 4
3.1.2 | IT support to database development and linkages | [13 empty] | YP/SR | Staff time | 4 | 24
| (a) Consolidation of database where possible into a central repository | [14 empty] | APW |  |  | 1 | 30000 |  | 33900
| (b) Cost of system and installation/implementation costs | [14 empty] | APW |  |  | 1 | 30000 |  | 33900
3.1.3 | Website software and server hosting | [13 empty] | YP/SR | Staff time | 4 | 6
| (a) Maintenance and development of STB distribution lists | [13 empty] | YP/SR | Staff time | 6 | 6
| (b) Maintenance and development of Stop TB web site | [13 empty] | YP/SR | Staff time | 10 | 60
| (c) Maintenance of communique and web alert | [13 empty] | SR | Staff time | 2 | 6
| (d) Hosting charges and cost of two web servers to support data | [14 empty] | APW |  |  | 1 | 60000 |  | 67800
3.1.4 | Information system products | [13 empty] | YP | Staff time | 60 | 12
| (a) Costs associated with software, implementation and support | [17 empty] | 3 | 30000 |  | 101700
3.1.5 | Partners database maintenance and strengthening | [13 empty] | YP/ML/GS | staff time | 12 | 24
| Sub-total | [19 empty] | 261708 | 237300
| 4.1 Community mobilization to support DOTS expansion | [12 empty] | DEWG/RO/CO/SMT/NTP | NV | Staff time
[16 empty] | P-staff | 44 |  |  | 120000 | 59664
[16 empty] | G-staff |  | 16 |  | 60000 | 10848
4.1.1 | Complete monitoring and evaluation of 3 COMBI plans in 3 initial HBCs | [13 empty] | NV, ML, EJ | Staff time | 2 | 4
| (a) Contract for monitoring and evaluation of the three countries, Bangladesh, India and Kenya | [14 empty] | APW |  |  | 1 | 100000 |  | 113000
4.1.2 | Develop COMBI best practices for ROs and NTPs | [13 empty] | NV | Staff time | 2 | 2
| (a) Contract to produce materials on best practices | [14 empty] | APW |  |  | 1 | 20000 |  | 22600
4.1.3 | Develop and implement COMBI training courses and promote COMBI in high burden countries | [13 empty] | NV, EJ, ML, | Staff time | 4 | 2
| (a) Training courses in Africa and Asia | [14 empty] | Training course |  |  | 3 | 30000 |  | 101700
4.1.4 | Production, duplication and distribution of documentary film in Bangladesh | [13 empty] | NV, ML, EJ | Staff time | 12 | 4 | 1
| (a) Contract to produce, duplicate and distribute documentary film | [14 empty] | APW |  |  | 1 | 50000 |  | 56500
4.1.5 | Production of booklet on COMBI I | [13 empty] | NV, ML | Staff time | 12 | 2
| (a) Production of booklet (design, printing and distribution) | [14 empty] | APW |  |  | 1 | 20000 |  | 22600
4.1.6 | Participate in DEWG country missions | [13 empty] | All | staff time | 12 | 2
| Sub-total | [19 empty] | 70512 | 316400
| 5.1 Evaluation, assessment and documentation | [12 empty] | DEWG/SMT/RO | ML | Staff time
[16 empty] | P-staff | 26 |  |  | 120000 | 35256
[16 empty] | G-staff |  | 8 |  | 60000 | 5424
5.1.1 | Development of COMBI assessment tools for NTPs | [13 empty] | EJ, ML, NV, PH | Staff time | 20 | 4
5.1.2 | Duplication and distribution of documentary film in Eastern Europe to ROs and NTPs | [13 empty] | ML | Staff time | 6 | 4
| (a) Duplication, distribution and promotion of film | [14 empty] | APW |  |  | 1 | 5000 |  | 5650
| Sub-total | [19 empty] | 40680 | 5650
| Sub-total for Staff costs and Activity costs | [14 empty] | FTEs 6.1 | 274 | 217 |  |  | 518670 | 1491600
| Total for Advocacy and Communications | [20 empty] | 2010270
A supplementary workplan with concrete details will be presented to the Coordinating Board in the course of 2003 for the following activities:
1 | Planning and implementation of COMBI in 6 additional high-burden countries with an estimated cost of USD1.8 million
2 | Global countdown campaign leading to 2005 - The pla n and budget to be presented after 2002 assessment.

## ANNEX 4
Stop TB Work Plan 2003
4 | Area of Work: Administration
2003
| Products and activities | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Linkages | Targets 2003 | Indicators | Means of Verification | Assumptions & Risks | TBP responsible | Component | FTE (P) | FTE (G) | No./Units | Unit Cost | Staff cost | Cost of Activities | Contributions in kind | Implementors
| 1.1 Administrative and logistical management of the partnership | [17 empty] | JK/LA | Staff time
[20 empty] | Staff time | 178 |  |  | 150000 |  | 301710
[20 empty] | P-staff | 178 |  |  | 150000 | 301710
[20 empty] | G-staff |  | 100 |  | 75000 | 84750
4.1.1 | Support and management of staff in the secretariat | [18 empty] | Staff time | 100 | 60
4.1.2 | Provision of office space and office equipment | [18 empty] | Supplies and equipment | 4 | 20 | 25 | 400 |  | 11300
4.1.3 | Monitoring of finances, budget and cash flows | [18 empty] | Staff time | 70 | 10 |  |  |  | 0
4.1.4 | Capacity and team building | [18 empty] | Training | 4 | 10 | 10 | 2500 |  | 28250
[20 empty] | Retreat |  |  | 2 | 5000 |  | 11300
[18 empty] | Sub-Total |  | Sub-total |  |  |  |  | 386460 | 50850
FTEs 3.5
[18 empty] | Grand Total | [7 empty] | 437310